ANANTASUTRA

The 365-Day War Plan

Dual-track: the Business Machine (MRR) + the Capital Machine (fundraising velocity) - daily targets, weekly gates, monthly kill-or-double decisions.

Day 1 = Monday, 17 August 2026 (Week 1). Founder's eyes only. Version 1.0.

THE PREMISE (from your own research)

Every sub-12-month unicorn ran on machines loaded BEFORE day one: founder pedigree monetized as a seed round, an insider cap table that re-marked itself, inherited distribution, and a capital-glut window. None of those exist here today - so this plan manufactures the equivalents while building the business underneath (the Zetwerk/Physics-Wallah discipline your research itself endorses):

Pedigree machine -> A prior exit is replaced by manufactured pedigree: accelerator imprimatur (YC/Peak XV Surge applications), strategic angels from the client network, and a metrics story nobody can argue with.

Inheritance machine -> Inherited assets are replaced by what already exists: the automation stack (3 daily pipelines), playbooks, signed contracts, referral network, and the India-GCC corridor.

Template machine -> The template story for investors: 'Deel for embedded experts' - a platform take-rate on managed talent payroll, fed by a PROFITABLE services engine. Template clones are what the fast cohort sold; ours has revenue under it.

Window -> Capital window: not controllable. The plan builds raise-readiness by Month 6 so that IF a window opens, we move in days. Raising from strength, never need.

Hard guardrails adopted from the failure cohort in your research: no leverage (Mensa/GlobalBees death), no fake or self-flattering metrics (GoMechanic/BharatPe), no revenue deferral (Koo), no building on regulatory forbearance (MPL). Violating any of these voids the plan.

THE TWO TRACKS AND THE YEAR IN ONE VIEW

| Month | Business gate (MRR / clients) | Capital gate |
| --- | --- | --- |
| M1 Sep | Rs 1.5L / 6 clients | Data room folder started; metrics dashboard live |
| M2 Oct | Rs 2.5L / 9 | YC + Surge applications filed; 10 angel relationships opened |
| M3 Nov | Rs 4L / 12 | First 3 advisor-angels closed (small cheques, big names) |
| M4 Dec | Rs 6L / 15 | Platform v0.1 internal; pitch narrative v1 tested on 5 investors |
| M5 Jan | Rs 8L / 18 | Accelerator interviews / decision; GCC entity groundwork |
| M6 Feb | Rs 10L / 22 | SEED ATTEMPT: Rs 2-4Cr at Rs 15-25Cr pre (only if metrics green) |
| M7 Mar | Rs 13L / 26 | Seed closed or bootstrapped-on; platform v1 to clients |
| M8 Apr | Rs 16L / 30 | PR cadence starts (funding/metrics story every 6 weeks) |
| M9 May | Rs 20L / 34 | Platform take-rate revenue line exists; NRR >110% proven |
| M10 Jun | Rs 25L / 38 | Series A narrative: corridor platform, 2 markets, 3x YoY |
| M11 Jul | Rs 30L / 42 | A-round conversations (target Rs 15-30Cr at Rs 80-150Cr) |
| M12 Aug | Rs 35L+ / 45+ | Day 365: Rs 4-5Cr ARR run-rate, platform live, priced by outsiders |

Honesty line: hitting Day 365 at Rs 4-5Cr ARR with a live platform and an outsider-priced round is a ~Rs 30-80Cr company and a genuine unicorn TRAJECTORY. The mark itself then depends on Series B/C velocity and a capital window - the two things no plan can schedule. Everything schedulable is below, day by day.

THE DAILY OPERATING SYSTEM - every day, all 365

The same seven numbers, logged every evening in the tracker (5 minutes). A day without the log is a failed day regardless of what else happened:

OWNER-CONTACTS: 20 decision-makers reached (calls/WhatsApp/DM per playbook. Not dials - owners.)

DISCOVERY CALLS: 2 held or booked (30-min, ends with 2-3 profiles promised)

PROPOSALS/FOLLOW-UPS: 1 proposal sent + every follow-up due today cleared (48h rule)

CONTENT: auto-pipelines verified green (7:33/8:33/9:03) + day's post published + article shipped (15-min human loop)

DELIVERY PULSE: every active client's channel checked; any red flag escalated same day

CAPITAL: 1 investor/angel/advisor touch (Mon-Fri) - a message, an update, a coffee, a metric shared

SCORE LOGGED: revenue in, cash out, pipeline moves - 5 minutes, every night

Sunday is the exception: no outreach - 60-minute weekly review (scorecard vs gates), plan the week, rest. Burnout is a plan-killer; the review is not optional, the rest is not optional.

THE 52 WEEKS - day-by-day targets

Six working days per week (Mon-Sat) + Sunday review. Daily OS applies always; lines below are ADDITIONAL day-specific targets. Weeks compound: nothing below repeats setup already done.

MONTH 1 - IGNITION (Weeks 1-4) | Gate: Rs 1.5L MRR, 6 clients, Awish <50%

WEEK 1  (Aug 17-22) - Referral detonation + pipeline restart

Mon: Awish referral meeting booked: ask Dr. for 2 named colleague intros; chase the Rs 15K Aug gap; Gaba contract signed & countersigned

Tue: 50-clinic call list built from leads pipeline (Tier A/B tagged); first 20 owner-contacts done; salesperson JD posted (Naukri+LinkedIn)

Wed: 20 contacts; 2 discovery calls target; Savetime upsell conversation (2nd seat / review pod)

Thu: 20 contacts; CA-partnership shortlist (5 firms) built; first CA meeting requested

Fri: 20 contacts; investor data-room folder created (contracts, P&L sheet, metrics); Wonder Gifts follow-up

Sat: Week tally: 100+ contacts, 6+ discoveries, 2 proposals out, 1 referral intro in motion; fix whatever number missed

WEEK 2  (Aug 24-29) - First new closes

Mon: Close attempt #1 (strongest discovery from W1) - contract same day if yes

Tue: Salesperson interviews (3 booked this week); 20 contacts

Wed: 20 contacts; 2nd CA meeting; Awish referral intro #1 discovery call

Thu: 20 contacts; proposal follow-ups; GCC list started (BotWot referral ask sent)

Fri: Metrics dashboard v1 live (MRR, clients, concentration %, pipeline) - this becomes the investor artifact

Sat: Close attempt #2; week tally vs targets; Sunday: Month-1 half-time review

WEEK 3  (Aug 31-Sep 5) - Salesperson onboard + volume

Mon: Salesperson hired (offer out); onboarding day 1 on playbook + shadowing your calls

Tue: 20 contacts (you) + 10 (trainee); clinic #2 target close

Wed: Combined 35 contacts/day from here; 3 discoveries

Thu: Angel list v1: 20 names (client-network strategics, corridor operators, micro-VCs) with warm paths

Fri: 35 contacts; proposal #5-6 out; PW-style proof asset: publish Awish case study page with real numbers

Sat: Week tally; salesperson week-1 scorecard; pipeline review

WEEK 4  (Sep 7-12) - Month-1 gate

Mon: Close week: every warm deal gets a close attempt Mon-Wed

Tue: 35 contacts; close attempts continue

Wed: GATE CHECK: Rs 1.5L MRR / 6 clients / Awish <50%? Miss by >30% -> Sunday = diagnosis day, fix before scaling

Thu: First angel coffee (no ask - show dashboard, ask for advice); 35 contacts

Fri: Month-2 client list built (60 targets incl. 10 GCC); content pillars reviewed against what converted

Sat: Month-1 books closed: P&L updated, tracker complete, one-page investor update #1 written (even with zero investors - discipline starts now)

MONTH 2 - MACHINE PROOF (Weeks 5-8) | Gate: Rs 2.5L MRR, 9 clients | Capital: YC + Surge filed

WEEK 5  (Sep 14-19) - Accelerator applications

Mon: YC application drafted (the story: profitable services engine -> Deel-for-embedded-experts platform; real numbers in)

Tue: Surge/accelerator application drafted; 35 contacts continue daily throughout

Wed: Applications reviewed by 2 trusted founders; revise

Thu: YC + Surge SUBMITTED; angel coffee #2-3 this week

Fri: Clinic pod #4-5 close attempts; GCC discovery #1 (BotWot referral)

Sat: Week tally; investor update #2; video-testimonial ask sent to Awish

WEEK 6  (Sep 21-26) - Second salesperson decision + GCC open

Mon: If salesperson #1 hit quota 2 weeks straight -> open req #2; else coach or replace (48h decision, own medicine)

Tue: GCC: 5 Dubai clinic/SME contacts via IBPC list; corridor pricing sheet made (AED)

Wed: 40 combined contacts; close attempt; Savetime review-pod upsell closed?

Thu: Awish video testimonial recorded (editor edits per skillset doc)

Fri: Testimonial live on site + LinkedIn; angel coffees #4-5

Sat: Week tally; Month-2 halfway check vs Rs 2.5L gate

WEEK 7  (Sep 28-Oct 3) - Referral engine formalized

Mon: Referral policy finalized (thank-you standard); ask made to EVERY active client this week

Tue: CA partnership #1 signed (rev-share or reciprocal); their first 3 intros requested

Wed: 40 contacts; discovery x3; proposal x2

Thu: Platform spec v0 written: expert DB + seat tracking + invoice split (from lived workflow, not imagination)

Fri: Dev hire/contract for platform v0.1 (or Lakshay allocated 50%); angel #6-7

Sat: Week tally; pipeline > Rs 4L in proposals outstanding?

WEEK 8  (Oct 5-10) - Month-2 gate

Mon: Close week Mon-Wed: every warm deal attempted

Tue: Close attempts; 40 contacts

Wed: GATE: Rs 2.5L / 9 clients? Concentration <40%? Publish investor update #3 with the curve

Thu: First platform v0.1 sprint demo (internal): expert DB live

Fri: Diwali-season pitch built for retail/jeweller segment (Gaba as reference client!)

Sat: Month-2 books closed; celebrate something with the team - publicly

MONTH 3 - TWELVE CLIENTS (Weeks 9-13) | Gate: Rs 4L MRR, 12 clients | Capital: 3 advisor-angels closed

WEEK 9  (Oct 12-17) - Diwali retail push

Mon: Jeweller/retail segment blitz begins (Gaba story): 15 targeted contacts/day in segment

Tue: 40 contacts; GCC discovery #2-3

Wed: Advisor-angel #1 term agreed (small cheque + name + intros)

Thu: 40 contacts; close attempt

Fri: Platform sprint: seat tracker demo; content: Diwali gifting angle live

Sat: Week tally; investor update #4

WEEK 10  (Oct 19-24) - Close + capital

Mon: Close week Mon-Wed

Tue: 40 contacts; advisor-angel #2

Wed: Close attempts; GCC proposal #1 out (AED)

Thu: Platform: invoice-split module (salary/fee line items automated)

Fri: Angel #3; PR seed: pitch one journalist the anti-markup story

Sat: Week tally

WEEK 11  (Oct 26-31) - Delivery hardening

Mon: Delivery audit: every client's 90-day target on track? Fix reds today

Tue: Coordinator #2 hired if >10 clients (Himanshu/Yash capacity rule: 6 clients each max)

Wed: 40 contacts; close

Thu: Bench audit: 2 vetted experts ready per pod type; hire gaps

Fri: 40 contacts; GCC close attempt #1

Sat: Week tally; churn check: zero tolerance review

WEEK 12  (Nov 2-7) - Scale contacts

Mon: Combined contact capacity to 50/day (you 10, sales team 40) - your calls become closes only

Tue: Close x2 attempted

Wed: Advisor-angels signed off: 3 names on site/deck

Thu: Platform v0.1 COMPLETE internal: all clients tracked in it

Fri: Investor update #5: show MRR curve + platform screenshot

Sat: Week tally

WEEK 13  (Nov 9-14) - Month-3 gate

Mon: Close week

Tue: Close week

Wed: GATE: Rs 4L / 12 clients / <35% concentration / 3 angels

Thu: Miss -> diagnosis protocol; Hit -> raise Month-4 targets 10%

Fri: Quarter-1 retrospective written (what converted, CAC by channel, churn)

Sat: Q1 books closed + team bonus if gate hit

MONTHS 4-6 - PRODUCTIZE + SEED (Weeks 14-26) | Gates: M4 Rs 6L/15 | M5 Rs 8L/18 | M6 Rs 10L/22 + SEED ATTEMPT

WEEK 14  (Nov 16-21) - Pods go fixed-price

Mon: Clinic Growth Pod productized: fixed Rs 60-90K/mo, 90-day outcome sheet, sellable by sales team alone

Tue: SME Pod + Review Pod (Gaba model) productized same way

Wed: 50 contacts; pods pitched to entire warm pipeline

Thu: Pitch narrative v1 drafted (deck: problem/markup, engine, platform, corridor)

Fri: Narrative tested on advisor-angels; brutal feedback

Sat: Week tally; investor update #6

WEEK 15  (Nov 23-28) - GCC beachhead

Mon: Dubai trip planned (Jan): IBPC event calendar, 15 meetings targeted

Tue: GCC client #1 closed? AED pricing live on site for corridor page

Wed: 50 contacts

Thu: Platform: client-portal wireframes

Fri: Accelerator interview prep (if shortlisted)

Sat: Week tally

WEEK 16  (Nov 30-Dec 5) - Month-4 gate

Mon: Close week

Tue: Close week

Wed: GATE: Rs 6L / 15 clients

Thu: Seed list built: 20 micro-VCs/seed funds for the corridor story

Fri: Update #7 goes to the 20 (metrics only, no ask): 'raising in Q1' whisper

Sat: Books; Q(uarter) planning

WEEK 17  (Dec 7-12) - Pipeline depth

Mon: 50 contacts; every pod pitched x10 this week

Tue: Platform client-portal dev sprint

Wed: Close x2

Thu: 2nd GCC close attempt

Fri: PR: first article placed or founder podcast recorded

Sat: Week tally

WEEK 18  (Dec 14-19) - Year-end close-out

Mon: Close everything warm before holidays: 5 attempts this week

Tue: Close

Wed: Close

Thu: Jan Dubai meetings confirmed (10+)

Fri: Holiday auto-pilot verified: pipelines + coordinators cover 10 days

Sat: Half-month tally

WEEK 19  (Dec 21-26) - Light week - strategy

Mon: Deep work: platform spec v1 final

Tue: Deep work: seed deck final draft

Wed: Family/rest (delivery skeleton crew)

Thu: Rest

Fri: Rest

Sat: Year review written: the Day-1-to-Day-130 curve, honestly

WEEK 20  (Dec 28-Jan 2) - Reload

Mon: Q3 target-setting with team

Tue: 60-contact/day capacity plan (hire #3 sales?)

Wed: M5 client list: 80 targets

Thu: Seed data room complete: contracts, books, metrics, cap table clean

Fri: Dubai bags packed - materials printed (AED pricing, corridor deck)

Sat: Week tally

WEEK 21  (Jan 4-9) - DUBAI WEEK

Mon: Dubai: 3 meetings/day + IBPC evening

Tue: Dubai: meetings

Wed: Dubai: meetings

Thu: Dubai: close attempt on the spot (7-day start is the wedge)

Fri: Dubai: investor/angel meetings (2 GCC angels)

Sat: Fly back; trip debrief: 15 meetings -> X discoveries -> Y proposals

WEEK 22  (Jan 11-16) - Dubai follow-through

Mon: Every Dubai meeting followed up <72h with proposal

Tue: 50 contacts resume

Wed: GCC closes #2-3 attempted

Thu: Platform beta: 3 friendly clients invited to portal

Fri: Seed deck v2 after Dubai learnings

Sat: Week tally; update #8

WEEK 23  (Jan 18-23) - Month-5 gate

Mon: Close week

Tue: Close week

Wed: GATE: Rs 8L / 18 clients / GCC = 2+ clients

Thu: Accelerator decision in? Plan either branch

Fri: Seed: 5 partner meetings requested for Feb

Sat: Books

WEEK 24  (Jan 25-30) - Seed sprint prep

Mon: Metrics one-pager: 6-month curve, cohort retention, NRR, CAC

Tue: Mock pitches x3 (advisors as VCs)

Wed: 50 contacts (machine never stops during raise - THE lesson)

Thu: Portal beta feedback -> fix list

Fri: Seed meetings booked: 8+ across Feb

Sat: Week tally

WEEK 25  (Feb 1-6) - SEED MEETINGS

Mon: Pitch #1-2

Tue: Pitch #3; sales machine 50/day continues via team

Wed: Pitch #4-5

Thu: Investor follow-ups same-day always

Fri: Pitch #6; term-sheet targets: Rs 2-4Cr at Rs 15-25Cr pre

Sat: Week tally; read the room honestly: heat or no heat?

WEEK 26  (Feb 8-13) - Month-6 gate + seed decision

Mon: Pitch #7-8 or term-sheet negotiation

Tue: GATE: Rs 10L MRR / 22 clients

Wed: SEED DECISION: term sheet at fair terms -> take it; lukewarm -> WALK, bootstrap on (PW rule: raise from strength or not at all)

Thu: Either way: announce something (round or milestone) - PR cadence begins

Fri: Platform v1 launch date set (March)

Sat: Half-year books: Rs 10L MRR = Rs 1.2Cr run-rate, likely profitable throughout - written up as update #9

MONTHS 7-9 - PLATFORM + COMPOUNDING (Weeks 27-39) | Gates: M7 Rs 13L/26 | M8 Rs 16L/30 | M9 Rs 20L/34 + NRR>110%

WEEK 27  (Feb 15-20) - Post-seed org

Mon: If funded: hire plan executed (2 sales, 1 dev, 1 ops in 30 days); if not: profit-funded slower version

Tue: 60 contacts/day capacity

Wed: Platform v1 sprint

Thu: Close x2

Fri: Update #10 (now monthly rhythm to real investor list)

Sat: Tally

WEEK 28  (Feb 22-27) - Platform v1 code-complete

Mon: Sprint

Tue: Sprint

Wed: QA with 5 clients

Thu: 60 contacts continue via team; you close only

Fri: Launch materials (demo video by your editor)

Sat: Tally

WEEK 29  (Mar 1-6) - PLATFORM LAUNCH

Mon: Portal live to ALL clients: KPIs, reports, invoices, replace-button

Tue: PR push: 'the agency markup is now a line item you can see' story pitched x5 outlets

Wed: Every prospect demo now includes portal (differentiation weapon)

Thu: Close x2

Fri: Founder LinkedIn launch post (the machine amplifies)

Sat: Tally

WEEK 30  (Mar 8-13) - Month-7 gate

Mon: Close week

Tue: Close week

Wed: GATE: Rs 13L / 26 clients

Thu: Take-rate model spec: fee becomes platform-billed

Fri: Seat-expansion campaign: every client offered seat #2 with portal data

Sat: Books

WEEK 31  (Mar 15-20) - Seat expansion

Mon: Expansion calls x5

Tue: 60 contacts; UK corridor test (Gaba referral ask into Southall network)

Wed: Close

Thu: Platform: automated review-collection module (Gaba pod, productized in software)

Fri: Update #11

Sat: Tally

WEEK 32  (Mar 22-27) - UK corridor

Mon: UK diaspora list: 30 targets via Gaba/Smile With Kris references

Tue: Close x2

Wed: 60 contacts

Thu: NRR measurement live in dashboard

Fri: PR #2 placed

Sat: Tally

WEEK 33  (Mar 29-Apr 3) - Month-8 gate

Mon: Close week

Tue: Close week

Wed: GATE: Rs 16L / 30 clients / 3 markets billing

Thu: Q4 plan

Fri: Team offsite (yes, spend the day)

Sat: Books

WEEK 34  (Apr 5-10) - Density

Mon: Clinic segment #2 city (Jaipur/Gurgaon dense push)

Tue: 60 contacts

Wed: Close x2

Thu: Platform: matching v0 (vetting scores searchable)

Fri: Update #12

Sat: Tally

WEEK 35  (Apr 12-17) - Ops hardening

Mon: Delivery audit all 30+ clients

Tue: Coordinator #3 if needed; playbook v2 from 8 months of calls

Wed: Close

Thu: Churn autopsy on any loss; fix systemically

Fri: Bench: 40+ experts

Sat: Tally

WEEK 36  (Apr 19-24) - Compound week

Mon: Close x2

Tue: 60 contacts

Wed: Referral harvest: every client asked again (now with portal to show)

Thu: CA partners #4-5

Fri: PR #3

Sat: Tally

WEEK 37  (Apr 26-May 1) - Pre-gate push

Mon: Close week

Tue: Close

Wed: Pipeline > Rs 8L outstanding?

Thu: A-narrative draft: 'corridor talent platform, 3x, profitable'

Fri: Update #13

Sat: Tally

WEEK 38  (May 3-8) - Month-9 gate

Mon: Close week

Tue: GATE: Rs 20L / 34 / NRR>110%

Wed: Miss -> focus diagnosis; hit -> A-prep greenlit

Thu: Platform take-rate revenue reported as separate line (investors' favourite line)

Fri: Books

Sat: Tally

WEEK 39  (May 10-15) - A-prep

Mon: A-list: 15 funds (corridor/B2B/marketplace theses)

Tue: Update #14 to A-list (no ask)

Wed: 60 contacts never stop

Thu: Close x2

Fri: Data room refresh

Sat: Tally

MONTHS 10-12 - SERIES A VELOCITY (Weeks 40-52) | Gates: M10 Rs 25L/38 | M11 Rs 30L/42 | M12 Rs 35L+/45+ & outsider-priced round

WEEK 40  (May 17-22) - Metrics theatre (honest version)

Mon: Cohort analysis published in update #15

Tue: Close x2

Wed: 60-70 contacts/day org-wide

Thu: Platform: self-serve demo env for investors

Fri: PR #4: platform milestone story

Sat: Tally

WEEK 41  (May 24-29) - Month-10 push

Mon: Close week

Tue: Close

Wed: GCC client #6-8 push (corridor proof for A)

Thu: Second GCC trip planned or virtual roadshow

Fri: Update #16

Sat: Tally

WEEK 42  (May 31-Jun 5) - Month-10 gate

Mon: Close

Tue: GATE: Rs 25L / 38

Wed: A-meetings requested x10

Thu: Advisor mock-pitches round 2

Fri: Books

Sat: Tally

WEEK 43  (Jun 7-12) - A-meetings wave 1

Mon: Pitch #1-2

Tue: Machine runs via team

Wed: Pitch #3-4

Thu: Follow-ups

Fri: Pitch #5

Sat: Read heat honestly; tally

WEEK 44  (Jun 14-19) - A-meetings wave 2

Mon: Pitch #6-7

Tue: Close x2 (business proof during raise = leverage)

Wed: Pitch #8-9

Thu: Partner dinners; corridor angels activated for intros

Fri: Pitch #10

Sat: Tally

WEEK 45  (Jun 21-26) - Term-sheet zone

Mon: Negotiations or regroup

Tue: Business close week regardless

Wed: GATE-CHECK Rs 27L+ trending

Thu: Term sheet: target Rs 15-30Cr at Rs 80-150Cr pre - ONLY at fair terms from outsider lead

Fri: Update #17

Sat: Tally

WEEK 46  (Jun 28-Jul 3) - Month-11 gate

Mon: Close week

Tue: GATE: Rs 30L / 42

Wed: Round decision: outsider-priced A, or profitable independence (both are wins; only bad outcome is a needy raise)

Thu: Platform roadmap Y2 written

Fri: Books

Sat: Tally

WEEK 47  (Jul 5-10) - Diligence / double-down

Mon: DD support or growth double-down

Tue: Close x2

Wed: 70 contacts org-wide

Thu: Hire wave planned against round or profit

Fri: PR #5

Sat: Tally

WEEK 48  (Jul 12-17) - Compound

Mon: Close week

Tue: Seat expansion round 3

Wed: UK/GCC/India all billing monthly - corridor proof complete

Thu: Platform: 100% of clients on portal

Fri: Update #18

Sat: Tally

WEEK 49  (Jul 19-24) - Pre-anniversary push

Mon: Close x3 attempted

Tue: Close

Wed: Team performance reviews + ESOP plan (real one, fair strikes - your research's Part 5 warning)

Thu: Y2 plan drafted

Fri: PR #6: the year-one story

Sat: Tally

WEEK 50  (Jul 26-31) - Month-12 sprint

Mon: Close week

Tue: Close week

Wed: Rs 33L+ trending check

Thu: Round paperwork or bootstrap celebration

Fri: Books

Sat: Tally

WEEK 51  (Aug 2-7) - Land the year

Mon: Close

Tue: Close

Wed: GATE: Rs 35L+ / 45+ clients

Thu: Every number audited honestly for the Day-365 report

Fri: Team celebration - the machine earned it

Sat: Tally

WEEK 52  (Aug 9-14) - DAY 365

Mon: Write the Day-365 report: MRR curve, clients, markets, platform seats, round status - all real

Tue: Compare to this document publicly with the team: hit, missed, learned

Wed: Y2 war plan drafted using the same machinery (now with 10x the data)

Thu: Investor update #19: the year in one chart

Fri: Decide the Y2 unicorn-path branch: A-funded platform sprint, or profitable compounding toward it

Sat: Rest. Then Day 366.

PROTOCOLS

Gate-miss diagnosis (any month >30% under)

Freeze scaling (no new hires/spend); 3-day diagnosis: pipeline volume, conversion, or churn - which broke?

Fix the ONE broken stage for 2 weeks before resuming; adjust the remaining gates honestly rather than pretending.

Kill rules

Channel with <1 client after 2 months of daily effort: killed.

Segment pod with <60% of 90-day targets hit across 3 clients: redesigned or killed.

Any client requiring fake metrics, review fraud, or fee games: fired, whatever the revenue.

The founder's calendar (what only Bhavya does)

Mornings: closes and investor meetings only. Afternoons: M1-3 selling -> M4-6 productizing -> M7-9 platform -> M10-12 raising.

Everything else has an owner by Month 3 or it doesn't happen. The plan fails if the founder is still doing delivery in Month 7.

The one-line summary: 365 days of 20 owner-contacts, 2 discoveries, 1 proposal, 1 investor touch, and 7 logged numbers - every single day - compounding through 12 monthly gates into a Rs 4-5Cr ARR platform company priced by outsiders. That is the fastest honest road that exists from here; the unicorn is what Years 2-4 do with it.